## Sheet1
EASFAA Goal | EASFAA Strategy | EASFAA Tactic and Committee Action Steps | Ownership TBD BY EC | Metrics | Start Date | Projected Completion Date | Estimated Committee Budget (If Applicable) | PROJECT ON SCHEDULE DELAYED ON HOLD | CANCELED
1. Training and Professional Development | 1.1 Provide robust and relevant training opportunities to the membership and foster collaborative training opportunities among member states through both in-person and webinar training. | 1.1.1 Continue to use evaluation feedback, membership surveys, and national trends to develop training topics and programs.
1.1.2 Continue robust training opportunities through various outlets such as: Annual Training, EASFAA Leads, NASFAA Credentials, and Tuesdays @2 Webinars.
1.1.3. Evaluate and assess member engagement and feedback in training events.
1.1.4 Focus and respond to the unique needs of our membership and the different strengths and needs of our partner states.
| 0 | 1.1.5 Reinvest in graduate/professional training and symposia
1.1.6 Provide training relevant to enhanced leadership skills such as project management.
1.1.7 Explore new and evolving training modalities.
1.1.8 Explore and invest in high-quality trainers.
| 1.2 Develop and maintain a training track dedicated to Diversity & Inclusion. (See also 3.2) | 1.2.1 Include Diversity & Inclusion training at the Annual Conference and through EASFAA Leads, Tuesdays @2, and Annual Training.
1.2.2. Collaborate effectively with NASFAA’s Diversity & Inclusion training and initiatives.
1.2.3 Pursue opportunities to partner with EASFAA state and other regional associations on diversity and inclusion training initiatives.
| 1.3. Provide an annual conference that rotates throughout the states in the region. | 1.3.1 Provide a program that includes relevant and rich training opportunities.
1.3.2 Provide opportunities for networking and relationship building.
1.3.3 Engage our membership with our vendor sponsors to share information about products and services.
| 1.4 Provide financial aid leadership development opportunities. | 1.4.1 Pursue opportunities to partner with NASFAA on leadership development and succession planning initiatives. For example, sponsor attendees to NASFAA's LLCE (based on tracks offered e.g. succession planning, and/or other PD tracks).
1.4.2 Pursue opportunities to partner with EASFAA state and other regional associations on leadership development and succession planning initiatives. (e.g. inter-regional visits, cross-association presentations).
1.4.3 Provide opportunities to increase Certified Financial Aid Administrator (FAAC) and NASFAA credentials among EASFAA members.
1.4.4 Continue and enhance EASFAA Leads, which provides training on leadership and management topics. (See also 1.1.2 and 2.1.4)
1.4.5. Explore the feasibility and potential impact of new EASFAA led professional development initiatives, such as internships, leadership coaching, and/or facilitated project planning teams to aid in succession planning.
2. Volunteer and Association Leadership Development | 2.1 Provide association leadership development opportunities. | 2.1.1 Identify and encourage potential leaders who are prepared to take leadership roles and cultivate the use of their abilities.
2.1.2 Develop an evaluation tool to identify those with leadership abilities and provide opportunities for association involvement.
2.1.3 Create various avenues for leadership development.
2.1.4. Continue and expand the Leadership Track for the annual conference that ties into EASFAA Leads. (See also 1.1.2 and 1.1.4)
2.1.5 Allow students to sign up for membership and encourage participation.
| 2.2 Expand mentoring opportunities | 2.2.1 Develop mentoring opportunities for new members.
2.2.2 Provide mentor training and resources.
2.2.3. Develop a series of webinars dedicated to new members.
| 2.3 Create volunteer opportunities in order to build a pipeline. | 2.3.1 Work to expand committee involvement and participation.
2.3.2 Engage volunteers in task forces/ad hoc committees to complete initiatives in a timely and focused manner.
2.3.3. Build succession strategies into committees, developing future, prepared leadership.
| 2.2: Expand mentoring opportunities. | 2.2.1 Develop mentoring opportunities for new members.
2.2.2 Provide mentor training and resources.
2.2.3 Develop a series of webinars dedicated to new members.
| 2.3 Create volunteer opportunities in order to build a pipeline. | 2.3.1 Work to expand committee involvement and participation.
2.3.2 Engage volunteers in task forces/ad hoc committees to complete initiatives in a timely and focused manner.
2.3.3 Build succession strategies into committees, developing future, prepared leadership.
| 2.4. Strategy: Create opportunities to fully engage EASFAA Executive Council state representatives. (See also 4.3) | 2.4.1. Build, implement, and sustain a consistent Executive Council onboarding experience for new state representatives.
2.4.2. Create networking opportunities for state representatives to collaborate and share best practices in state association leadership.
2.4.3. Evaluate opportunities for state representatives to participate in standing and/or ad hoc EASFAA committees
3 Diversity and Inclusion | 3.1 EASFAA Board of Directors and Committees should be reflective of the diversity of the organization. | 3.1.1Increase membership and volunteerism from diverse populations.
| 3.2 Continue and expand the training track dedicated to Diversity & Inclusion. . (See also 1.2) | 3.2.1 Include Diversity & Inclusion training at the Annual Conference and through EASFAA Leads, Tuesdays @2, and Annual Training.
3.2.2 Collaborate effectively with NASFAA’s Diversity & Inclusion training and initiatives.
3.2.3. Pursue opportunities to partner with EASFAA state and other regional associations on diversity and inclusion training initiatives.
3.2.4. Secure experts to address and facilitate discussion on relevant diversity and inclusion topics
| 3.3 Building a mentoring program that focuses on establishing a pipeline to increase diverse membership. | 3.3.1 Provide opportunities for each member state association to sponsor or recommend potential committee members and/or committee chairs.
3.3.2 Engage specifically with HBCUs and MSIs in the region.
| 3.4 To increase the diversity of speakers and presenters through training and presenters | 3.4.1. Seek out and secure diverse speakers and presenters for both in-person and virtual events.
3.4.2. Provide coaching and/or mentoring to diverse subject-matter experts to encourage sharing expertise as presenters and/or trainers
3.4.3. Evaluate opportunities to sponsor NASFAA credentials for diverse subject-matter experts. (See also 1.4.3)
3.4.4. Secure experts to address and facilitate discussion on relevant diversity topics with the EASFAA Executive Council.
4. Enhanced Public Footprint | 4.1. Goal: Actively establish partners on advocacy. | 4.1.1 Collaborate and strategize with NASFAA when appropriate.
4.1.2 Partner with NASFAA on the Advocacy Pipeline efforts.
4.1.3 Actively communicate and work with state association presidents and/or federal advocacy committee chairs.
4.1.4 Utilize Executive Council leadership on direct engagement with ED and legislative staff.
| 4.2 Engage, inform, and empower membership on advocacy. | 4.2.1 Poll members for “hot button” or topics of interest on advocacy.
4.2.2 Prepare and distribute briefing materials related to topics of interest to the association.
4.2.3 Provide listening or strategy sessions on topics of interest to the association.
4.2.4. Provide resources to help develop advocacy skills and involvement.
| 4.3 Strengthen member-state relationships . (See also 2.4) | 4.3.1. Create networking opportunities for state representatives to collaborate and share best practices in state association leadership
4.3.2. Facilitate inter-state collaboration such as providing networking opportunities for member-state committee chairs.
5. Operational Improvements | 5.1 Improve the membership experience. | 5.1 Launch annual membership renewal drive, including encouraging full use of institutional membership and outreach to define the value of membership.
5.1.2. Evaluate, plan, and implement expanded membership functionality, such as allowing individuals to add themselves to a member institution's roster.
5.1.3. Ensure that membership application/database captures all desired demographics about institutions and members, e.g. full sector list.
| 5.2. Provide enhanced communication functionality to members | 5.2.1. Create an enhanced communication platform for member engagement.
5.2.2 Provide opportunities for new and seasoned member engagement.